## Sheet1
Task | Estimate 8/16 | Time Remaining 8/18 | Time Remaining 8/23 | Time Remaining 8/24 | Time Remaining 8/25 | Time Remaining 8/26 | Actual
Console Project Design and WireFrame | 8 | 6 | 0 | 0 | 0 | 0 | 6
Console Project Dto's | 6 | - | 0 | 0 | 0 | 0 | 0.5
Console Project Service Layer | 10 | - | 12 | 8 | 3 | 0 | 8
Console Project UI Layer | 10 | - | 6 | 6 | 3 | 0 | 10
Testing and Revision | - | - | 4 | 4 | 4 | 2 | 4
total hours | 34 | 6 | 22 | 18 | 10 | 2 | 28.5
Available Hours
2016-08-22 | 2016-08-23 | 2016-08-24 | 2016-08-25 | 2016-08-26
M | T | W | TH | FR | ttl available
6 | 6 | 3 | 8 | 5.5 | 28.5